Potential SOW

Protective Factors for Youth Substance Abuse and Delinquency in CA

The Role of Expanded Learning Programs

Background and Context:

California recently passed Proposition 64, legalizing the adult use of recreational marijuana. The campaign to pass proposition 64 relied heavily on messages that additional revenue, specifically 60% of the revenue generated by the proposition, would support youth programs, especially after school programs. However, once passed, revenue for after school programs was left out of the statute. It is imperative that California’s expanded learning field provide evidence from compelling research and data highlighting how such an infrastructure is an effective vehicle to achieve the proposition’s spirit and goals of funding for youth programs.

Description of Final Product:

A document similar to Alaska’s Protective Factors for Youth Substance Abuse and Delinquency: The Role of Afterschool Programs that surfaces and provides a meta-analysis of research outlining that after school programs are an effective approach to substance use prevention and delinquency. Make connections to how expanded learning could be a vehicle to achieve the goals of the priorities for youth funding generated by Proposition 64.

Potential Scope of Work:

Participate in planning meeting with advisory group to provide further context to inform the final document (estimated 3 hours prep and implementation). The meeting will serve to identify and/or validate the research questions to be addressed through this work including but not limited to the following: - How do expanded learning programs in California define the work of the development of protective factors with their youth? - How do expanded learning programs in California address the development of protective factors through their daily practices? - What practices are used in the work to support the development of youth resiliency?

Review the priorities for youth funding outlined in Proposition 64.

Review Alaska’s document Protective Factors for Youth Substance Abuse and Delinquency: The Role of Afterschool Programs and surface California-specific data sets such as California Healthy Kids Survey, California Public Health Data, and California Department of Education data that are equivalent to the sources utilized in the Alaska report

Provide a general overview of California’s expanded learning system, pulling from existing documents such as the State of Expanded Learning in CA as well as data that outlines: - How California’s expanded learning infrastructure intersects with communities most impacted by the war on drugs (low-income communities and communities of color), - How California’s expanded learning infrastructure intersects with schools with high foster youth and homeless youth populations, and - How California’s expanded learning infrastructure / programs operate in communities that see higher than average rates of dropouts.

Review and analyze national and California-specific data that includes but is not limited to: - Surgeon General Risk and Protective Factors - California Healthy Kids Survey - www.Kidsdata.org - Other data equivalents surfaced in the review described above.

Review research that might include and may not be limited to (depending on advisory group input): - WestEd’s model of Positive Youth Development and supporting research included in Resiliency: What we have learned. - Create a theoretical correlation between the Quality Standards for Expanded Learning in California and Positive Youth Development Protective Factors.

Surface research-based approaches as to how high-quality after school and summer learning programs are/can: - Be an effective protective factor in and of themselves by operating in the critical hours of 3-6, and in the summer. - Generate protective factors by providing environments rich in positive youth development protective factors.

Create a draft document including bibliography of supporting research and data sources.

Participate in two rounds of reviews, input, and edits from the advisory group

Submit to CAN a final report integrating input and suggested edits from the advisory group